Project Design Phase
Problem – Solution Fit Template
Date
07 NOV 2025
Team ID
NM2025TMID07047
Project Name
Garage Management System
Maximum Marks
4 Marks
Product Backlog, Sprint Schedule, and Estimation (4 Marks)
Functional
User
Story
Team
Sprint
Requirement
User Story / Task
Priority
Points
Members
(Epic)
Number
Customer &
As an admin, I can register
Sprint-
N. Durga
Vehicle
USN-1
new customers and their
3
High
1
Mahendra
Registration
vehicles in the system.
As a garage manager, I can
Service
add and manage different
R. S. S.
Category
USN-2
2
High
service
categories
(e.g.,
Manoj
Management
repair, wash, maintenance).
As a manager, I can assign
N.
Job Assignment
USN-3
jobs to mechanics based on 3
High
Gowtham
skill and availability.
As an admin, I can update
Sprint- Inventory
USN-4
and monitor spare parts
4
High
O. Sravani
Tracking
inventory.
As a cashier, I can generate
Sprint- Billing and
N. Durga
USN-5
invoices and manage
Medium
Payment
Mahendra

---
payments after services.
As a customer, I can receive
Sprint- Notification
SMS or email notifications
USN-6
R. Kiran
System
about service status and
completion.
As a manager, I can generate
Sprint- Reports &
USN-7
daily/weekly reports and
Low
Feedback
view customer feedback.
Project Tracker, Velocity & Burndown Chart (4 Marks)
Total
Story Points
Sprint End
Sprint Release
Duration
Start
Completed (as on
Date (Planned)
Date (Actual)
Planned End Date)
01 NOV
15
6 Days
06 NOV 2025
15
06 NOV 2025
2025
07 NOV
18
6 Days
12 NOV 2025
18
12 NOV 2025
2025
13 NOV
20
6 Days
18 NOV 2025
19
18 NOV 2025
2025
19 NOV
15
6 Days
24 NOV 2025
15
24 NOV 2025
2025
Velocity Calculation
Average Velocity = (Total Story Points Completed) / (Total Duration in Days)
= (67 Story Points) / (24 Days) = 2.79 Points/Day
Burndown Chart
A Burndown Chart represents the work remaining versus time across sprints.
In this project, tasks such as registration, job management, billing, and reporting are tracked to
ensure continuous progress.
It helps the team maintain timely delivery and identify workflow bottlenecks.

---
References:
https://www.visual-paradigm.com/scrum/what-is-agile-software-development
https://www.atlassian.com/agile/tutorials/burndown-charts
https://www.atlassian.com/agile/tutorials/sprints https://www.atlassian.com/agile/project-
management/estimation